## Cover
TEST PLAN
Project Name | Test_Facebook |  |  | Reviewer | Lê Minh Quân
Project Code | FB_COM_TEST |  |  | Review date | 2024-11-01
Creator | Lê Minh Quân |  |  | Approver | Lê Minh Quân
Version | v1.0 |  |  | Approval Date | 2024-11-01
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-26 | v1.0 | Initial |  |  |  | s
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
ProlTM_ScreenDesign_v0.5 |  |  |  | 0.5
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Lê Minh Quân
2 | Create test design |  |  | Lê Minh Quân
3 | Create test cases |  |  | Lê Minh Quân
4 | Create test data |  |  | Lê Minh Quân
5 | Execute system test |  |  | Lê Minh Quân
6 | Defects list |  |  | Lê Minh Quân
7 | Create test report |  |  | Lê Minh Quân
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-11-01 | Lê Minh Quân | Teacher | This document itself
2 | Test cases | 2024-11-08 | Lê Minh Quân | Teacher
3 | Defect logs | 2024-11-15 | Lê Minh Quân | Teacher
4 | Test report | 2024-11-22 | Lê Minh Quân | Teacher
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Le Minh Quan | Le Minh Quan | Le Minh Quan
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the Test_Facebook system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | Test_Facebook_v1.0
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop |  |  |  | Standard Fsoft
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | Lê Minh Quân | Member | Đọc và phân tích tài liệu, viết test design, test case, defect log, test report.
2 | Huỳnh Bảo Huyền Ngọc | Member
3 | Võ Nguyễn Nhật Khương | Member
4 | Phan Ái Nhung | Member
5 | Danh Phước Toàn | Member
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-26 | 2024-11-01
2 | Create test design | 2024-10-26 | 2024-11-01
3 | Create test case | 2024-11-02 | 2024-11-08
4 | Execute test and log bugs | 2024-11-09 | 2024-11-15
5 | Evaluting exit criteria & Test report | 2024-11-16 | 2024-11-22
6 | Review | 2024-11-23 | 2024-11-29
| Task | Start day from 26/10/2024 | Duration
| Create test plan | 0 | 6
| Create test design | 0 | 6
| Create test case | 7 | 6
| Execute test and log bugs | 14 | 6
| Evaluting exit criteria & Test report | 21 | 6
| Review | 28 | 6
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October | November
|  |  | 26 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Lê Minh Quân
2 | Create test design | Lê Minh Quân
2019-01-02 | Hiển thị giao diện đăng bài | Lê Minh Quân
2019-02-02 | Điều hướng trong trang đăng bài | Lê Minh Quân
2019-03-02 | Lựa chọn đói tượng và thuộc tính bài viết | Lê Minh Quân
2019-04-02 | Kiểm tra đăng bài với các nội dung khác nhau | Lê Minh Quân
2019-05-02 | Kiểm tra đăng bài với các trường hợp đặc biệt | Lê Minh Quân
2019-06-02 | Tương tác và phản hồi người dùng | Lê Minh Quân
2019-07-02 | Thông báo khi thao tác | Lê Minh Quân
2019-08-02 | Kết quả sau khi đăng bài | Lê Minh Quân
3 | Create test case | Lê Minh Quân | bar: November 2 to November 8
2019-01-03 | Hiển thị giao diện đăng bài | Lê Minh Quân | bar: November 2 to November 8
2019-02-03 | Điều hướng trong trang đăng bài | Lê Minh Quân | bar: November 2 to November 8
2019-03-03 | Lựa chọn đói tượng và thuộc tính bài viết | Lê Minh Quân | bar: November 2 to November 8
2019-04-03 | Kiểm tra đăng bài với các nội dung khác nhau | Lê Minh Quân | bar: November 2 to November 8
2019-05-03 | Kiểm tra đăng bài với các trường hợp đặc biệt | Lê Minh Quân | bar: November 2 to November 8
2019-06-03 | Tương tác và phản hồi người dùng | Lê Minh Quân | bar: November 2 to November 8
2019-07-03 | Thông báo khi thao tác | Lê Minh Quân | bar: November 2 to November 8
2019-08-03 | Kết quả sau khi đăng bài | Lê Minh Quân | bar: November 2 to November 8
4 | Execute test and logs bug | Lê Minh Quân | bar: November 9 to November 15
2019-01-03 | Hiển thị giao diện đăng bài | Lê Minh Quân | bar: November 9 to November 15
2019-02-03 | Điều hướng trong trang đăng bài | Lê Minh Quân | bar: November 9 to November 15
2019-03-03 | Lựa chọn đói tượng và thuộc tính bài viết | Lê Minh Quân | bar: November 9 to November 15
2019-04-03 | Kiểm tra đăng bài với các nội dung khác nhau | Lê Minh Quân | bar: November 9 to November 15
2019-05-03 | Kiểm tra đăng bài với các trường hợp đặc biệt | Lê Minh Quân | bar: November 9 to November 15
2019-06-03 | Tương tác và phản hồi người dùng | Lê Minh Quân | bar: November 9 to November 15
2019-07-03 | Thông báo khi thao tác | Lê Minh Quân | bar: November 9 to November 15
2019-08-03 | Kết quả sau khi đăng bài | Lê Minh Quân | bar: November 9 to November 15
5 | Evaluting exit criteria & Test report | Lê Minh Quân | bar: November 16 to November 22
6 | Review | Lê Minh Quân | bar: November 23 to November 29

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14